## Project Status Report
PROJECT STATUS REPORT TEMPLATE
PROJECT NAME | Third Charm Studios Mining Game | PROJECT CODE | n/a
PROJECT MANAGER | Shay | DATE OF STATUS ENTRY | 2024-04-29
PERIOD COVERED | 04/08/2024-04/29/2024 | PROJECTED DATE OF COMPLETION | 2024-05-10
PROJECT STATUS THIS WEEK
OVERALL PROJECT STATUS | POTENTIAL RISKS / DELAYS
SUMMARY | Overall, Game is mostly on-schedule for completion. Levels and Code are being discussed in team discord. Potential game title not created.
MILESTONES | 04/23/2024 Player Sprite sheet created, 04/24/2024 Enemy sprites created. 04/29/2024 Timeline completed. Also, see team Github Project: https://github.com/users/ShayGraziano2004/projects/1
PROJECT COMPONENTS
COMPONENT | STATUS | OWNER / TEAM | NOTES
BUDGET | ON | Samantha L | Zero dollars needed.
RESOURCES | UP-TO-DATE | Shay, Brady, and Samantha
TIMELINE | IN PROGRESS | Shay, Brady, and Samantha | On track to having working game by due date.
SCOPE | IN PROGRESS | Shay, Brady, and Samantha | Discussing what is needed for working model by due date. Cautioned against too much dependency on graphics.
WORK ACCOMPLISHED
TASK NUMBER | DESCRIPTION | OWNER / TEAM | RECEPTION
1 | Design Game Story | All
2 | Design Game Assets | All
3 | Design Levels | All
4 | Create HUD and Cutscenes
RISKS AND ROADBLOCKS
RISK NUMBER | DESCRIPTION | OWNER / TEAM | FIX
1 | Levels not clearly defined. | All | Clarifying on discord. Tile sets created.
2 | Potential delay of code due to finishing Zelda Assignment | All
3
4
HIGHLIGHTS AND KEY TAKEAWAYS
Asset creation is on schedule. Code creation a little behind, but should be made up by end of day Wednesday, 05/01/2024.
PROJECT SCHEDULE
TASK | STATUS | DETAILS
Game Storyline | COMPLETE | See also Third Charm Team Planning Github Project Page
Design Assets | UP-TO-DATE | Player sprite sheet created. Some enemy sprites created. Tile sets created.
Design Levels | OVERDUE | Levels are vague. Will get updated expectation on first level by 05/01/2024
Script Events for game | IN PROGRESS
Create HUD and Cutscenes | UP-TO-DATE | Ideas for HUD and opening and exiting cut scenes are being discussed and shouldn't be a problem.
Special FX and cleanup | HOLD | Clean up should be fine. Special effects may be out of project scope/may need to be reduced.
OVERDUE
OVERDUE
PROJECT TIMELINE
MILESTONE 1
Come up with game idea.
MILESTONE 2
Come up with development timeline. Understand code creation.
MILESTONE 3
Asset creation.
MILESTONE 4
Code creation and level design.
MILESTONE 5
CURRENT TIMELINE POSITION
04/29/2024
ROADBLOCK 1.
Had not finalized project timeline. Updated Timeline on 04/29/2024. See Github Project Page.
ROADBLOCK 2
unknown
PROJECT START DATE
04/08/0000
PROJECT END DATE
05/10/2024

## Dropdown Keys - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
OVERALL STATUS KEY | BUDGET KEY | GENERAL STATUS KEY
ROADBLOCK / OVERAGE | OVER | OVERDUE
POTENTIAL RISKS / DELAYS | ON | UP-TO-DATE
ON TRACK | UNDER | HOLD
COMPLETE
IN PROGRESS

## Project Description
Project Overview
In our game, you play as a courageous dwarf miner who ventures into the depths of a newly revealed cave system.
An earthquake has just shaken an old, believed-to-be-tapped-out mine, uncovering paths into previously unexplored natural caverns.
These caverns hold precious ores, but they're also home to dangerous subterranean creatures and treacherous traps.